## Lead
ONLINE MOVIE TICKET BOOKING
Group Number - 10
Team Lead & Frontend Lead- Akula.Keerthi Naga Sai Sri
Backend Lead - Mayank Tiwari

## Status Track
Project Status Check Report Team - 10
Sl no. | Employee ID | Name | Domain | Module | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-25 | 2023-09-26 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08
1 | 2567234 | Mayank | Back-end,Front-end | user | Read and Understand Problem Statement | Customer Purchase(user) | Customer controller,ui,customer model | Databse configuration | Postman,Unittesting,Integration | ppt prepation,issue solving | preparing for presentation
2 | 2568358 | Pachaiyappan | Back-end,Front-end | user | Read and Understand Problem Statement | Order Summary,Previous Order(user) | Product Controller,Sevice ,Model | costumer repo,model,DB | Postman,Unittesting,Integration | ppt prepation,issue solving | preparing for presentation
3 | 2569162 | Abhishek | Back-end,Front-end | admin | Read and Understand Problem Statement | Add,Edit,delete Movie(Admin) | Admin Controller,Service,Model | Add movie,edit(ui),DB | Postman,Unittesting,Integration | ppt prepation,issue solving | preparing for presentation
4 | 2566784 | Keerthi | Back-end,Front-end | admin | Read and Understand Problem Statement | Admin login,Admin Page | Admin Controller,Service,Model | AdminModel,repo | Postman,Unittesting,Integration | ppt prepation,issue solving | preparing for presentation
5 | 2567606 | Archana | Back-end,Front-end | admin | Read and Understand Problem Statement | Admin Account creation | product controller,Sevice ,Model | Product Model,repo | Postman,Unittesting,Integration | ppt prepation,issue solving | preparing for presentation
6 | 2567148 | Raghu | Back-end,Front-end | admin | Read and Understand Problem Statement | Search and filter movies, movie dashboard | costumer controller,Service,Model | costumer model,repo | Postman,Unittesting,Integration | ppt prepation,issue solving | preparing for presentation
7 | 2567783 | Ranjan | Back-end,Front-end | user | Read and Understand Problem Statement | Login,home,registration(user) | cart controller,Service,Model | cart model,repo | Postman,Unittesting,Integration | ppt prepation,issue solving | preparing for presentation
8 | 2567360 | Pavan | Back-end,Front-end | admin | Read and Understand Problem Statement | Manage Purchase,Active order(Admin) | purchase controller,Service,Model | purchase Model ,repo | Postman,Unittesting,Integration | ppt prepation,issue solving | preparing for presentation
9 | 2568383 | Supriya | Back-end,Front-end | user | Read and Understand Problem Statement | adding cart ,payment page(user) | cart Controller,Service,Model | Cart model,repo | Postman,Unittesting,Integration | ppt prepation,issue solving | preparing for presentation
10

## Status Meeting
Status Meeting Group - RLL10
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2023-09-19 | 9:30 | a | 2:30 | a | 6:20 | a
2023-09-20 | 9:30 | a | 1:00 | a | 6:20 | a
2023-09-21 | 9:30 | a | 2:00 | a | 6:10 | a
2023-09-22 | 9:30 | a | 3:00 | a | 6:30 | a
2023-09-23 | 9:30 | a | 1:30 | a | 5:00 | a
2023-09-24 | 9:30 | a | 3:00 | a | 6:00 | a
2023-09-25 | 9:30 | a | 2:30 | a | 7:00 | a
2023-09-26 | 9:30 | a | 3:00 | a | 7:00 | a